## manual-testing-report-testcases
Test Case ID | Feature | Test Steps | Expected Result | Actual Result | Status (Pass/Fail) | Tester Name | Test Date | Remarks
MT_001 | User Login | Open /auth/login; Enter valid email & password; Click Login | User should be logged in and redirected based on role | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_002 | User Login | Open /auth/login; Leave email empty; Enter password; Click Login | Validation message shown: Email or Password is missing | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_003 | User Login | Open /auth/login; Enter email; Leave password empty; Click Login | Validation message shown: Email or Password is missing | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_004 | User Login | Open /auth/login; Enter unregistered email; Enter any password; Click Login | Error message shown: User Not Found | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_005 | User Login | Open /auth/login; Enter registered email; Enter wrong password; Click Login | Error message shown: Wrong Creditails | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_006 | User Signup (User) | Open /auth/signUp; Select User; Enter Name/Email/Password/Confirm (valid); Click Create | Account created; redirected to /auth/login?signupSuccess=true; success toast shown | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_007 | User Signup (Developer) | Open /auth/signUp; Select Developer; Enter Name/Email/Password/Confirm (valid); Click Create | Developer account created; redirected to login with success toast | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_008 | User Signup | Open /auth/signUp; Leave required fields missing; Click Create | Validation message shown: Some fields are missing | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_009 | User Signup | Open /auth/signUp; Enter password != confirmPassword; Click Create | Validation message shown: Passwords do not match | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_010 | User Signup | Open /auth/signUp; Enter password < 8 chars; Click Create | Validation message shown: Password must be at least 8 characters | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_011 | User Signup | Open /auth/signUp; Enter Age = 11; Fill other fields; Click Create | Validation message shown: Age must be between 12 and 60 | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_012 | User Signup | Open /auth/signUp; Enter Age = 61; Fill other fields; Click Create | Validation message shown: Age must be between 12 and 60 | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_013 | User Signup | Open /auth/signUp; Use an email that already exists; Click Create | Error message shown: User already exists | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_014 | Logout (User) | Login as user; Click logout icon; Confirm Yes | User should be logged out and redirected to / | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_015 | Logout Cancel | Login; Click logout icon; Click Cancel | User remains logged in; stays on current page | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_016 | Session Persistence | Login; Refresh browser tab | User stays logged in (role restored via cookie/API) | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_017 | Unauthorized API Access | Clear cookies; Try opening /user/profile (or call GET /api/v1/user) | Unauthorized error; profile data not loaded | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_018 | Forgot Password (Email required) | Open /auth/forgotPassword; Click Send Reset Link with empty email | Validation message shown: Email is required | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_019 | Forgot Password (Invalid email) | Open /auth/forgotPassword; Enter invalid email; Click Send Reset Link | Validation message shown: Please enter a valid email address | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_020 | Forgot Password (Success screen) | Open /auth/forgotPassword; Enter valid email; Click Send Reset Link | Shows 'Check Your Email' success screen | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_021 | Forgot Password (Resend) | After success screen; Click Resend | Returns to form; email cleared | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_022 | Theme Toggle (Global Navbar) | From any page; Click theme toggle icon | Theme switches dark/light; persisted in cookie 'theme' | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_023 | Landing Page Load | Open / | Home page loads; navbar + sections visible; no blocking errors | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_024 | About Page | Open /about | About content renders correctly | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_025 | Blog Page | Open /blog | Blog placeholder loads | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_026 | Games Page (Featured) | Open /games?category=featured | Featured games grid loads | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_027 | Games Page (Invalid category) | Open /games?category=unknown | Fallback category renders (featured) | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_028 | One-Tap Game (Flappy Bird) Load | Open /one-tap/flappy-bird | Flappy Bird iframe loads; Back button returns to / | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_029 | Footer Links (Missing pages) | Click footer: Privacy/Terms/Contact | Should navigate; if 404, log defect 'page missing' | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_030 | Home Approved Games Load | Ensure at least 1 approved game exists; Open / | Approved games from backend render as cards | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_031 | Home Pagination Next | On / with >1 page; Click Next | Moves to next page; game list updates | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_032 | Home Pagination Previous | On / page>1; Click Previous | Moves to previous page; game list updates | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_033 | Home No Approved Games | Ensure there are zero approved games; Open / | Dynamic games grid hidden; page still loads | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_034 | Home Backend Down | Stop backend; Open / | Error toast shown: Failed to fetch games | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_035 | Play Button Route | On /; Click Play on a backend-fetched game | Should navigate to playable page; if 404, log defect '/game/[id] missing' | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_036 | Developer Dashboard Load | Login as developer; Open /developer/dashboard | Dashboard loads; stats shown; table shows games or empty message | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_037 | Developer Upload Page Load | Login as developer; Open /developer/upload | Upload form renders | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_038 | Developer Upload Required Validation | On upload form; leave fields empty; Submit | Error: All fields are required | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_039 | Developer Upload Desc Min | Enter desc <8 chars; Submit | Error: Description must be at least 8 characters | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_040 | Developer Upload Desc Max | Enter desc >500 chars; Submit | Error: Description must be less than 500 characters | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_041 | Developer Upload New Game | Enter valid title/desc/genre; Submit | Game created with status pending; redirect to /developer/dashboard | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_042 | Developer Upload Duplicate Title | Create game with an existing title; Submit | Error: Game already Existed | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_043 | Developer Edit Game Prefill | From /developer/dashboard click a game row | Navigates to /developer/upload?id=<id>; form prefilled | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_044 | Developer Update Game | On edit page; update title/desc/genre; Click Update | Game updated; success; reflected in dashboard | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_045 | Developer Upload Cancel | On upload page; Click Cancel | Returns to /developer/dashboard | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_046 | Developer Upload File Picker UI | On upload page; select a file | File name & size displayed on button/caption | Same as Expected Result | Pass | Areena | 2025-01-14 | Test passed successfully
MT_047 | Admin Dashboard Load | Login as admin; Open /admin/admin | Pending games table loads; stats cards show totals | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_048 | Admin Pending Pagination | On /admin/admin with >1 page; click Next/Previous | Pending games list paginates correctly | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_049 | Admin Pending Search | On /admin/admin; enter search keyword | List updates after debounce; shows matching pending games | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_050 | Admin Approve Pending Game | On /admin/admin; Click Approve | Game status becomes approved; removed from pending list; stats updated | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_051 | Admin Reject Pending Game (Cancel) | Click Reject; Cancel confirm | Game not deleted; remains pending list | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_052 | Admin Reject Pending Game (Confirm) | Click Reject; Confirm Yes | Game deleted; removed from list; stats updated | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_053 | Admin Logout (Sidebar) | Login as admin; On /admin/admin click Sidebar Logout; Confirm Yes | Admin should be logged out and redirected to / | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_054 | User Profile Load | Login as user; Open /user/profile | Profile fields populated (name/email/age) | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_055 | Developer Profile Load | Login as developer; Open /developer/profile | Profile fields populated (name/email/age) | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_056 | Profile Update Success | On profile; update name/email/age; Click Save Changes | Success toast; data updated | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_057 | Profile Update Age Low | Set age to 11; Save | API rejects (age must be above 12) OR error shown | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_058 | Profile Update Age High | Set age to 61; Save | API rejects (age must be below 60) OR error shown | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_059 | Change Password Required Fields | Open profile; leave password fields empty; Save Changes | Error: All fields are required | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_060 | Change Password Mismatch | Enter newPassword != confirmPassword; Save | Error: Passwords do not match | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_061 | Change Password Length | Enter newPassword <8; Save | Error: Password must be at least 8 characters | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_062 | Change Password Success | Enter valid newPassword & confirm; Save | Password updated; toast shown; fields cleared | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_063 | Login With New Password | After changing password; logout; login with new password | Login succeeds | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_064 | Upgrade Page Load | Login as user; Open /user/upgrade | Upgrade page loads with Free and Premium cards | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_065 | Upgrade Button Behavior | On /user/upgrade; Click Upgrade to Premium | Expected to navigate to payment module; if only console log, log gap | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_066 | API Play Game Unique Count | POST /api/v1/game/playgame {gameId} twice as same user | 200 both times; totalPlayedBy increases only once | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_067 | API Play Game Missing gameId | POST /api/v1/game/playgame {} | 400 Game ID is required | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_068 | Security: No Token Protected Route | Clear cookies; call GET /api/v1/user | 401 Token Not Found | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_069 | Security: Tampered Token | Edit token cookie to invalid; call protected API | 401 Unauthorized Access | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_070 | Security: Role Bypass Attempt | Login as user; call GET /api/v1/game/stats | 403 Forbidden | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_071 | Recovery: Backend Restart | Login; stop backend; refresh; start backend; refresh | App shows error while down; recovers after backend up | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_072 | Swipe Back Navbar (User) | Login as user; Go to /user/home; Swipe/drag right to go back | Navigates back to /auth/login; login page shows landing navbar (Home/Discover/About + Login/Sign Up) only | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully
MT_073 | Swipe Back Navbar (Developer) | Login as developer; Go to /developer/developer_home; Swipe/drag right to go back | Navigates back to /auth/login; login page shows landing navbar (Home/Discover/About + Login/Sign Up) only | Same as Expected Result | Pass | Lea | 2025-01-14 | Test passed successfully